## Connect project plan template
Task name | Description | Task owner | Due date | Start date | Status | Dependency | VST comments | Customer comments
Check-in meeting scheduled |  | VST
Shared key sent to VS | Public SSH
SFTP folder created |  | VST |  |  |  | Shared key sent to VS
Test enrollment file sent to VS | [5 empty] | Shared key sent to VS, SFTP folder created
Verify test enrollment file |  | VST |  |  |  | Shared key sent to VS, SFTP folder created, Test enrollment file sent to VS
Script created to send daily enrollment | [5 empty] | Shared key sent to VS, SFTP folder created, Test enrollment file sent to VS, Verify test enrollment file
LMS setup instructions + values sent to LMS admin |  | VST
LTI tool installed in LMS | [5 empty] | LMS setup instructions + key values sent to LMS admin
LTI values sent to VST (client and deployment IDs if 1.3) | [5 empty] | LMS setup instructions + key values sent to LMS admin, LTI tool installed in LMS
LTI Testing |  | VST and client |  |  |  | LMS setup instructions + key values sent to LMS admin, LTI tool installed in LMS
LTI links placed in courses in LMS |  | LMS/Faculty? |  |  |  | LMS setup instructions + key/secret sent to LMS admin, LTI tool installed in LMS
Platform integration installed ** | [5 empty] | LMS setup instructions + key/secret sent to LMS admin, LTI tool installed in LMS, Developer key created and sent to VS
Key values created and sent to VST
Booklist confirmed
Branding | Bookshelf and Launch | VST
Connect training 1 | Connect users | VST
Welcome emails created in Connect | [5 empty] | Connect training 1
Connect training 2 | Connect users | VST
Items created in Connect | [5 empty] | Connect training 2
Connect training 3 | Connect users | VST |  |  |  | Items created in Connect
Courses matched in Connect | [5 empty] | Connect training 3
Items verified/sections active | [5 empty] | Items created in Connect, Connect training 3
Courses open in LMS
Communication with students
Connect training 4 | Connect users | VST
Communication with faculty
Catalog activated | [5 empty] | Items created in Connect, LTI links placed in courses in LMS, Script created to send daily enrollment, Courseware set up, Courses matched in Connect, Items verified/sections active
Welcome emails sent to students | [5 empty] | Welcome emails created in Connect, LTI links placed in courses in LMS, Script created to send daily enrollment, Courseware set up, Courses matched in Connect, Items verified/sections active, Communication with students, Communication with faculty, Catalog activated
Courseware set up | If Courseware needed | LMS admin & faculty
*Access codes, codeless, partner integration | If needed
Students bursar account billed | Date
Invoice sent to school |  | VST
Recap meeting |  | VST
Manage training
Bookshelf and Instructor Dash training
Outage notifications*** | Which outages